## Gantt Chart
ByteRacers
PROJECT TITLE |  | CEN 4090L Capstone Project |  |  |  |  | DATE | [6 empty] | 2025-08-25
TEAM MEMBERS |  | PUT NAMES HERE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | Sprint 1 | [14 empty] | Sprint 2 | [14 empty] | Sprint 3 | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | 1 | 2 | 3 | 4 | 5 | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 1 | 2 | 3 | 6 | 7 | 8 | 9 | 10 | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Group Formation and Project Selection
| Project start |  | 2025-08-26 | 2025-11-21 |  | 100% | bar: WEEK 1 1 M
Idea Selection | bar: WEEK 1 1 M to WEEK 1 4 R; WEEK 2 8 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 5 3 F
2 | Game Requirment Specifications
| SDL3 Configuration |  | 2025-09-01 | 2025-09-05 | 4 | 0% | bar: WEEK 1 1 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 5 3 F
| C++ Familiarization |  | 2025-09-01 | 2025-09-05 | 4 | 0% | bar: WEEK 1 1 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 5 3 F
| Game developement/ Design Principles |  | 2025-09-01 | 2025-09-05 | 4 | 0% | bar: WEEK 1 1 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 5 3 F
| End to End Game Workflow |  | 2025-09-01 | 2025-09-16 | 15 | 0% | bar: WEEK 1 1 M to WEEK 3 16 T; WEEK 5 29 M to WEEK 5 3 F
| Game mechanics / User Interface Mechanism |  | 2025-09-01 | 2025-09-16 | 15 | 0% | bar: WEEK 1 1 M to WEEK 3 16 T; WEEK 5 29 M to WEEK 5 3 F
3 | Environment Setup
| Overview of the game |  | 2025-09-01 | 2025-09-12 | 11 | 0% | bar: WEEK 1 1 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 5 3 F
| Game Menus (No Graphical Interface) |  | 2019-09-30 | 2019-10-25 | 25 | 0% | bar: WEEK 2 8 M to WEEK 6 10 F
| Game Loop (No Graphical Interface) |  | 2019-10-21 | 2019-11-15 | 24 | 0% | bar: WEEK 2 8 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 9 31 F
4 | Explicit Game Development
| Menu Navigation System |  | 2019-09-25 | 2019-10-02 | 7 | 0% | bar: WEEK 2 8 M to WEEK 3 17 W; WEEK 5 29 M to WEEK 5 3 F
| Simply Level Design |  | 2019-09-25 | 2019-10-02 | 7 | 0% | bar: WEEK 2 8 M to WEEK 3 17 W; WEEK 5 29 M to WEEK 5 3 F
Player Control System | bar: WEEK 2 8 M to WEEK 3 17 W; WEEK 5 29 M to WEEK 5 3 F
| Player Ability System |  | 2019-09-25 | 2019-10-11 | 16 | 0% | bar: WEEK 2 8 M to WEEK 5 3 F
| NPC / Enemy Control System |  | 2019-09-25 | 2019-10-11 | 16 | 0% | bar: WEEK 2 8 M to WEEK 5 3 F
5 | Module Development
| Menu Design |  | 2019-10-02 | 2019-10-25 | 23 | 0% | bar: WEEK 2 8 M to WEEK 6 10 F
| Level Design / Layout |  | 2019-10-02 | 2019-10-25 | 23 | 0% | bar: WEEK 2 8 M to WEEK 6 10 F
| Player Model Design |  | 2019-10-02 | 2019-10-25 | 23 | 0% | bar: WEEK 2 8 M to WEEK 6 10 F
| Ability Design |  | 2019-10-02 | 2019-10-25 | 23 | 0% | bar: WEEK 2 8 M to WEEK 6 10 F
| NPC / Enemy Design |  | 2019-10-02 | 2019-10-25 | 23 | 0% | bar: WEEK 2 8 M to WEEK 6 10 F
| Score System / Memory |  | 2019-10-07 | 2019-11-01 | 24 | 0% | bar: WEEK 2 8 M to WEEK 2 12 F; WEEK 4 22 M to WEEK 8 24 F
6 | Testing Evalutations
| Unit testing |  | 2019-10-07 | 2019-11-01 | 24 | 0% | bar: WEEK 2 8 M to WEEK 2 12 F; WEEK 4 22 M to WEEK 8 24 F
| Integration testing |  | 2019-10-21 | 2019-11-22 | 31 | 0% | bar: WEEK 2 8 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 11 14 F
| Product testing |  | 2019-11-11 | 2019-12-06 | 25 | 0% | bar: WEEK 2 8 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 5 3 F; WEEK 8 20 M to WEEK 12 21 F
7 | Integration
| Entity Graphic Integration |  | 2019-10-01 | 2019-10-16 | 15 | 0% | bar: WEEK 2 8 M to WEEK 2 12 F; WEEK 3 16 T to WEEK 5 3 F
| Dynamic Graphics |  | 2019-10-08 | 2019-11-01 | 23 | 0% | bar: WEEK 2 8 M to WEEK 2 12 F; WEEK 4 23 T to WEEK 8 24 F
| Audio, Scoring with movements |  | 2019-10-21 | 2019-11-22 | 31 | 0% | bar: WEEK 2 8 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 9 28 T
8 | Final Delivery
| Delivery |  | 2019-11-27 | 2019-12-06 | 9 | 0% | bar: WEEK 2 8 M to WEEK 2 12 F; WEEK 5 29 M to WEEK 5 3 F; WEEK 10 7 F to WEEK 12 21 F

## Form Responses 1
Timestamp | Untitled Question